## Sample Workplan for Vouchers
Sample: Voucher Workplan
ACTIVITY | SUB ACTIVITY | RESPONSIBLE | Month 1 |  |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  |  | Month 4 |  |  |  | Jan |  |  |  |  | Feb |  |  |  |  | Mar |  |  |  |  | Month 5 |  |  |  |  | Month 6 |  |  |  | Month 7 |  |  |  |  | Month 8 |  |  |  | Month 9
|  |  | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5
Laying the Foundation | Create Standard Operating Procedures outlining rules and responsbilities | Prog, Finance, Ops
| Pilot kick-off meeting with Finance, Procurement: intro to the pilot plan, roles and responsibilities, voucher cycle and redemption process and supporting tools | Prog
| Establish Community Accountability Reporting Mechanisms (CARMs) | Prog, M&E
| Establish M&E Plan | Prog, M&E
Determining the Voucher Type, Amount & Disbursement Mechanism | Conduct baseline market price survey | Prog or Ops
| Determine voucher type and estimation of the voucher value (based on market assessement, HH survey, FGD or estimated value of the typical in-kind basket distributed) | Prog
| Create voucher design | Prog, Finance
| Print vouchers | Procurement
| Determine mechanism (e-voucher or paper voucher) | Program
Identifying & Registering Program Participants | Community meeting to provide selection criteria | Program
| Conduct program participant verification, if necessary | Program
| Register program participants | Program
| Review CARMs regularly | Program and/or M&E
Selecting & Contracting Vendors | Design the vendors selection strategy (establishing targeting and outreaching criteria) | Program or Ops
| Hold community meetings to allow them input into the vendor selection criteria | Program
| Announce program opportunity for vendors, include the criteria, the application process and deadline for applying. | Program or Ops
| Vendor application or tender process | Program or Ops
| Vendor Scoring (cash vouchers) | Prog, Ops
| Price negotiation with vendors (commodity vouchers only) | Ops
| Sign contracts with vendors | Program, Ops
Designing & Printing Vouchers | Choose fraud-resistant design features and assign serial numbers | Program
| Tender process for selecting voucher printer (if external printing) | Ops
| Print vouchers | Ops
| Voucher intake to Finance | Finance, Ops
Training | Design training for program participants and vendors | Program
| Create training materials (if needed) | Program
| Prepare training materials for vendors | Program
| Prepare training materials for participants | Program
| Train vendors | Program
| Train participants | Program
Distribution | Develop Distribution Plan | Program
| Develop or adjust monitoring tools | M&E
| Each staff distributing vouchers requests release of vouchers from Finance | Program
| Finance updates Voucher Inventory Sheets | Program
| Prepare distribution materials | Program
| Inform vendors and participants of distribution dates | Program
| Distribute vouchers | Program
| Complete Distribution Monitoring Form | Program and/or M&E
| Complete Voucher Distribution Form | Program
| Return any undistributed/damanged vouchers to Finance | Program
| Finance destroys any damaged vouchers | Finance
| Finance conducts month-end voucher count | Program, Finance, M&E
Redemption | Adust/development monitoring tools | Program and/or M&E
| Monitor redemptions | Program and/or M&E
| Conduct Post-distribution Monitoring (PDM) with HHs, vendors, and key informants | Program and/or M&E
Reconciliation | Vendors submit redeemed vouchers and Voucher Redemption/Summary Sheet to MC Finance | Vendors, Finance
| Finance and Programs review and sign off on redeemed vouchers | Finance, Prog
| Finance initiates vendor payments | Finance
| Update Voucher Redemption Summary | Program
End-of-Program Transition | Final Evaluation | Prog and/or M&E