## Instructions
Instructions: Voucher Distribution Plan
When to use this form:
The Voucher Distribution Plan is used to plan your program's distributions and summarize all distributions in the program. You may alter it to create a more detailed plan per distribution location (including exact days/times).
Who is responsible for this form: |  | Who receives copies of this form:
Program |  | Finance
Operations
How to use this form:
This workbook contains two templates, completed as sample forms: the Summary Plan and the Detailed Plan. The Summary Plan should record all planned distributions for the entire program. You may complete the Detailed Plan in two ways. 1) If your program does not include many distributions, you may record each individual distribution on one sheet. 2) If you prefer - or if your program is large - we recommend making a separate Detailed Plan for each region. In partnership with Finance, you will develop a tracking system for each distribution, tracking at two levels. 1) The first level is a Reference Number that you assign to each town/ village/ neighborhood (whatever your smallest grouping is for program participants). 2) The second level tracks each distribution for each group assigned a Reference Number. For example, you assign a different Reference Number to each town, and program participants in each town receive four distributions over a period of four months. You need a Reference Number to differentiate the towns and then also a Distribution Number to differentiate each distribution per town. Town A = Reference # 10001 Town A, Distribution #1 = Distribution Number 10001.1 Town A, Distribution #2 = Distribution Number 10001.2 Town A, Distribution #3 = Distribution Number 10001.3 Town A, Distribution #4 = Distribution Number 10001.4 Town B = Reference # 10002 Town B, Distribution #1 = Distribution Number 10002.1 (and so on) You will carry over the Distribution Number (i.e. 10001.1) to every tool with a space for Distribution Number (i.e. Voucher Distribution List, Voucher Request Form, Voucher Distribution Monitoring Form and the Post-distribution Monitoring Household Survey). If multiple villages will go to one distribution point to receive their vouchers, it will complicate your tracking system, which you may want to document in Standard Operating Procedures (SOPs) or a Note to File. You need to be able to track your program participants to each of their distributions throughout the program and link their documents. If the dates/times/locations of distributions change, you need to be sure to update the Distribution Plan since it is linked to multiple other documents. Also, if the M&E plan is affected by the change in dates/times/locations, be sure to update it with any changes.
Where to file this form:
This form should be filed in the Program File: Implementation --> 4. Deliverables --> a. Description of Deliverables

## Summary Plan
Example: Voucher Distribution Plan - Summary
Program Title: ______________________________________________________ | [6 empty] | Program Cost Center:__________________________________
S.No | Distribution Number | District | Community | Number of Distributions | Distribution Date(s) | Number of Program Participants | Voucher Type | Voucher Value (cash and restricted cash vouchers only) | Voucher Contents (commodity vouchers only) | Notes
Example | 32XXXVD12345 | North | Community A | 3 | September 2014 October 2014 November 2014 | 1750 | Cash | USD 35
| 32XXXVD12346 | South | Community Y | 3 | October 2014 November 2014 December 2014 | 1200 | Cash | USD 35 |  | Can't start distributions in Community Y because the rainy season will block roads until October.
| 32XXXVD12347 | South | Community Y | 1 | February 2015 | 1200 | Commodity |  | 1 - shovel 1 - plow 25kg - seeds | Commodity vouchers will be distributed to Community Y the month before planting season.
TOTAL |  |  |  | 7 |  | 4150

## Detailed Plan
Example: Voucher Distribution Plan - Detailed Plan
Program Title: _______________________________________________________________________ | [7 empty] | Program Cost Center:__________________________________
S.No | Distribution Number | Staff Members Responsible for Distribution | District | Community | Distribution Date | Distribution Time | Number of Program Participants | Voucher Type | Voucher Value (cash and restricted cash vouchers only) | Voucher Contents (commodity vouchers only) | Notes
Example | 32XXXVD12345.01 |  | North | Community A | 2014-09-03 | 9:00 - 12:00am | 1750 | Cash | USD 35
| 32XXXVD12345.02 |  | North | Community A | 2014-10-04 | 8:30 - 11:30am | 1750 | Cash | USD 35
| 32XXXVD12345.03 |  | North | Community A | 2014-11-04 | 9:30am - 12:30pm | 1750 | Cash | USD 35
| 32XXXVD12346.01 |  | South | Community Y | 2014-10-05 | 2:30 - 4:30pm | 1200 | Cash | USD 35
| 32XXXVD12346.02 |  | South | Community Y | 2014-11-04 | 3:30 - 5:30pm | 1200 | Cash | USD 35
| 32XXXVD12346.03 |  | South | Community Y | 2014-12-02 | 8:00 - 10:00am | 1200 | Cash | USD 35
| 32XXXVD12347 |  | South | Community Y | 2015-02-08 | 8:30 - 10:30am | 1200 | Commodity |  | 1 - shovel 1 - plow 25kg - seeds